## Project Purpose Worksheet
Status Report
Project |  | Status: (Red/Yellow/Green)
Date: | 2022-04-20 | Overall Status: | Green
Contact: | lskpg@uw.edu | Explanation: | Completed planning Milestone
Prepared By: | Leslie Pang
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
1. Reviewed project data and organized them by fact and dimensional types.
2. Sketched out visualization dashboards and planned out desired metrics and filters.
3. Drafted and submitted ERD.
ID # | Key Issues/Blockers | Action Plan |  |  | Status
1 | Installing Snowflake |  |  |  | Open
Critical Milestones |  | Health | Due Date | Comment/Status
Planning |  | G | 2022-04-20 | Completed plans for this phase.
Design |  | G | 2022-05-02 | Beginning
Implementation |  | G | 2022-05-22 | Not started
Visualization |  | G | 2022-05-29 | Not started
Presentation |  | G | 2022-06-05 | Not started
G
G
G